## TUCG-1
		T			24	25	26
					T	T	T	24	24	24	24	25	25	25	25	26	26	26	26
	R ‘000	Total			2024	2025	2026	24Q1	24Q2	24Q3	24Q4	25Q1	25Q2	25Q3	25Q4	26Q1	26Q2	26Q3	26Q4
R00	Total	4,423,775			1,284,423	2,522,352	617,000	153,820	524,718	239,761	366,124	419,304	878,694	674,219	550,135	449,717	147,877	19,406	0

R01	Drilling EPC	326,580			143,739	182,841	0				143,739	84,837	98,004
R02	Early works EPC	56,711			21,402	35,309	0				21,402	18,296	17,013
R03	Civil EPC	161,257			0	138,720	22,537					44,641	56,243	37,836	22,537
R04	SMPP EPC	784,827			0	619,168	165,659					137,543	222,632	143,753	115,240	130,540	35,119
R05	E&I EPC	828,010			0	678,968	149,042					306,066	221,199	151,703	82,801	66,241
R06	Engines	1,150,830			575,415	460,332	115,083		345,249	115,083	115,083	115,083	115,083	115,083	115,083	115,083
R07	Interface Works	155,102			0	108,571	46,531					31,020	31,020	46,531	46,531
R08	EPC/M & Special	275,870			142,596	83,618	49,656	43,473	31,202	39,097	28,824	21,689	21,404	21,404	19,121	17,979	17,979	13,698
R09	Indirect Costs	380,511			220,695	91,324	68,492	91,322	45,661	45,661	38,051	22,831	22,831	22,831	22,831	34,246	28,538	5,708
R10	Owners Cost	95,125			76,100	19,025	0	19,025	19,025	19,025	19,025	19,025
R11	Insurance, duties	208,952			104,476	104,476	0		83,581	20,895				62,686	41,790

	USD @R18.50	18.50
D00	Total	239,122,973			69,428,270	136,343,351	33,351,351	8,314,595	28,363,135	12,960,054	19,790,486	22,665,081	47,496,973	36,444,270	29,737,027	24,309,027	7,993,351	1,048,973
D01	Drilling EPC	17,652,973			7,769,676	9,883,297	0	0	0	0	7,769,676	4,585,784	5,297,514	0	0	0	0	0
D02	Early works EPC	3,065,459			1,156,865	1,908,595	0	0	0	0	1,156,865	988,973	919,622	0	0	0	0	0
D03	Civil EPC	8,716,595			0	7,498,378	1,218,216	0	0	0	0	0	2,413,027	3,040,162	2,045,189	1,218,216	0	0
D04	SMPP EPC	42,423,081			0	33,468,541	8,954,541	0	0	0	0	7,434,757	12,034,162	7,770,432	6,229,189	7,056,216	1,898,324	0
D05	E&I EPC	44,757,297			0	36,700,973	8,056,324	0	0	0	0	0	16,544,108	11,956,703	8,200,162	4,475,730	3,580,595	0
D06	Engines	62,207,027			31,103,514	24,882,811	6,220,703	0	18,662,108	6,220,703	6,220,703	6,220,703	6,220,703	6,220,703	6,220,703	6,220,703	0	0
D07	Interface Works	8,383,892			0	5,868,703	2,515,189	0	0	0	0	0	1,676,757	1,676,757	2,515,189	2,515,189	0	0
D08	EPC/M & Special	14,911,892			7,707,892	4,519,892	2,684,108	2,349,892	1,686,595	2,113,351	1,558,054	1,172,378	1,156,973	1,156,973	1,033,568	971,838	971,838	740,432
D09	Indirect Costs	20,568,162			11,929,459	4,936,432	3,702,270	4,936,324	2,468,162	2,468,162	2,056,811	1,234,108	1,234,108	1,234,108	1,234,108	1,851,135	1,542,595	308,541
D10	Owners Cost	5,141,892			4,113,514	1,028,378	0	1,028,378	1,028,378	1,028,378	1,028,378	1,028,378	0	0	0	0	0	0
D11	Insurance, duties	11,294,703			5,647,351	5,647,351	0	0	4,517,892	1,129,459	0	0	0	3,388,432	2,258,919	0	0	0

S01	Pre				8Jan24	31Jan24		Jan24
	Engineering				1Feb24	9May25		1Feb24					9May25
	Implementation				8Jan24	7May26		8Jan24					7May26
	Commercial & Procurement				8Mar24	27Jun25		8Mar24					27Jun25
	Early Works Implementation				4Oct24	20Jun25					4Oct24		20Jun25
	Structural				31Jan25	7May26						31Jan25					7May26
	Mechanical				31Jan25	7May26						31Jan25					7May26
	Piping				31Jan25	21Apr26						31Jan25					21Apr26
	Electrical				17Mar25	21Apr26						17Mar25					21Apr26
	Control & instrumentation				26May25	7May26						26May25				7May26
	Civil & Buildings				16May25	23Feb26						16May25			23Feb26
	Commissioning				8May26	13Oct26						8May26		13Oct26
	Cold Com (Start)				1May26	1May26						1May26
	Hot Com (Start)				17Jul26	17Jul26						17Jul26
	Ramp Up				20Jul26	13Oct26						20Jul26	13Oct26
	RFC (Ready for Commissioning)				7May26	7May26						7May26
	RFO (Ready for Operation)				17Jul26	17Jul26						17Jul26
	BO (Beneficial Operation)				13Oct26	13Oct26						13Oct26

## TUCG-Pg
				T			24	25	26
				T	T	T	24	24	24	24	25	25	25	25	26	26	26	26
				R ‘000 (NPV)	Total			2024	2025	2026	24Q1	24Q2	24Q3	24Q4	25Q1	25Q2	25Q3	25Q4	26Q1	26Q2	26Q3	26Q4
1	G1T		R00	Pg1Pj1 Total	3,585,099			991,982	2,041,008	552,109	279,202	220,000	325,543	167,237	171,423	649,387	741,641	478,557	368,097	162,665	21,347	0

		G1T	R01	Drilling EPC	326,580			326,580	0	0			195,948	130,632					326,580
		G1T	R02	Early works EPC	56,711			21,402	35,309	0				21,402	18,296	17,013					56,711
		G1T	R03	Civil EPC	161,257			0	138,720	22,537					44,641	56,243	37,836	22,537				161,257
		G1T	R04	SMPP EPC	784,827			0	619,168	165,659					137,543	222,632	143,753	115,240	130,540	35,119			784,827
		G1T	R05	E&I EPC	828,010			0	678,968	149,042					306,066	221,199	151,703	82,801	66,241			828,010
		G1T	R06	Engines	115,083			0	115,083	0					115,083					1,150,830
		G1T	R07	Interface Works	124,082			0	77,551	46,531					31,020	46,531	46,531				155,102
		G1T	R08	EPC/M& Special	133,654			43,473	40,525	49,656	43,473					21,404	19,121	17,979	17,979	13,698		275,870
		G1T	R09	Indirect Costs	205,476			91,322	45,662	68,492	91,322					22,831	22,831	34,246	28,538	5,708		380,511
		G1T	R10	Owners Cost	19,025			19,025	0	0	19,025					95,125
		G1T	R11	Insurance, duties	104,476			0	104,476	0					62,686	41,790					208,952
		G1T	R12	Enterprise Dev’mt	400,000			400,000	0	0	100,000	200,000	100,000					100,000
		G1T	R13	Conttingency	325,918			90,180	185,546	50,192	25,382	20,000	29,595	15,203	15,584	59,035	67,422	43,505	33,463	14,788	1,941

				USD @R18.50	18.50
			D00	Pg1Pj1 Total	193,789,141			53,620,659	110,324,768	29,843,714	15,092,000	11,891,892	17,596,908	9,039,859	9,266,103	35,102,011	40,088,697	25,867,957	19,897,157	8,792,686	1,153,870
			D01	Drilling EPC	17,652,973			17,652,973	0	0	0	0	10,591,784	7,061,189	0	0	0	0	0	0	0
			D02	Early works EPC	3,065,459			1,156,865	1,908,595	0	0	0	0	1,156,865	988,973	919,622	0	0	0	0	0
			D03	Civil EPC	8,716,595			0	7,498,378	1,218,216	0	0	0	0	0	2,413,027	3,040,162	2,045,189	1,218,216	0	0
			D04	SMPP EPC	42,423,081			0	33,468,541	8,954,541	0	0	0	0	7,434,757	12,034,162	7,770,432	6,229,189	7,056,216	1,898,324	0
			D05	E&I EPC	44,757,297			0	36,700,973	8,056,324	0	0	0	0	0	16,544,108	11,956,703	8,200,162	4,475,730	3,580,595	0
			D06	Engines	6,220,703			0	6,220,703	0	0	0	0	0	0	0	6,220,703	0	0	0	0
			D07	Interface Works	6,707,135			0	4,191,946	2,515,189	0	0	0	0	0	0	1,676,757	2,515,189	2,515,189	0	0
			D08	EPC/M& Special	7,224,541			2,349,892	2,190,541	2,684,108	2,349,892	0	0	0	0	0	1,156,973	1,033,568	971,838	971,838	740,432
			D09	Indirect Costs	11,106,811			4,936,324	2,468,216	3,702,270	4,936,324	0	0	0	0	0	1,234,108	1,234,108	1,851,135	1,542,595	308,541
			D10	Owners Cost	1,028,378			1,028,378	0	0	1,028,378	0	0	0	0	0	0	0	0	0	0
			D11	Insurance, duties	5,647,351			0	5,647,351	0	0	0	0	0	0	0	3,388,432	2,258,919	0	0	0
			D12	Enterprise Dev’mt	21,621,622			21,621,622	0	0	5,405,405	10,810,811	5,405,405	0	0	0	0	0	0	0	0
			D13	Conttingency	17,617,195			4,874,605	10,029,524	2,713,065	1,372,000	1,081,081	1,599,719	821,805	842,373	3,191,092	3,644,427	2,351,632	1,808,832	799,335	104,897

			S01	Pre				8Jan24	31Jan24		Jan24
				Engineering				1Feb24	9May25		1Feb24					9May25
				Implementation				8Jan24	7May26		8Jan24					7May26
				Commercial & Procurement				8Mar24	27Jun25		8Mar24					27Jun25
				Early Works Implementation				4Oct24	20Jun25					4Oct24		20Jun25
				Structural				31Jan25	7May26					31Jan25					7May26
				Mechanical				31Jan25	7May26					31Jan25					7May26
				Piping				31Jan25	21Apr26					31Jan25					21Apr26
				Electrical				17Mar25	21Apr26					17Mar25					21Apr26
				Control & instrumentation				26May25	7May26					26May25				7May26
				Civil & Buildings				16May25	23Feb26					16May25			23Feb26
				Commissioning				8May26	13Oct26					8May26		13Oct26
				Cold Com (Start)				1May26	1May26					1May26
				Hot Com (Start)				17Jul26	17Jul26					17Jul26
				Ramp Up				20Jul26	13Oct26					20Jul26	13Oct26
				RFC (Ready for Commissioning)				7May26	7May26					7May26
				RFO (Ready for Operation)				17Jul26	17Jul26					17Jul26
				BO (Beneficial Operation)				13Oct26	13Oct26					13Oct26

				Pg1: 50MW Gas Engine PowerGen
				Pg2: 150MW Gas Engine Carbon Copies
				Pg3: 300MW Turbine PowerGen
				Pg4: 1950bbl GTL					Cash Flow: Programmes 1-4
				2024 – 2026 (USD):	230.9 m					Month	R’000	USD’m	Fact
				USD	USD	USD	Rand				Rand				Rand				Total		Dec23		18.50
				USD (Pg1-4):	2.87 bn			80.8 m	120.2 m	29.9 m	1,495.3 m				2,222.9 m				552.9 m					4,271,102.3	230,870.4
				Pg Total Rand):	53.09 bn					.28 bn	.23 bn	.35 bn	.63 bn	.22 bn	.70 bn	.79 bn	.52 bn	.37 bn	.16 bn	.02 bn	.00 bn	4.27 bn		Y2024	1,495,315.3	80,827.9
				Pg1 Total:	3.59 bn					.28 bn	.22 bn	.33 bn	.17 bn	.17 bn	.65 bn	.74 bn	.48 bn	.37 bn	.16 bn	.02 bn	.00 bn	3.59 bn		Jan24	56,896.4	3,075,481	0.2
				Pg2 Total:	12.00 bn					.00 bn	.00 bn	.00 bn	.00 bn	.00 bn	.00 bn	.00 bn	.00 bn	.00 bn	.00 bn	.00 bn	.00 bn	.00 bn		Feb24	85,344.6	4,613,222	0.3
				Pg3 Total:	30.00 bn					.00 bn	.01 bn	.02 bn	.20 bn	.00 bn	.00 bn	.00 bn	.00 bn	.00 bn	.00 bn	.00 bn	.00 bn	.22 bn		Mar24	142,241.0	7,688,703	0.5
				Pg4 Total:	7.50 bn					.00 bn	.00 bn	.01 bn	.22 bn	.04 bn	.04 bn	.04 bn	.04 bn	.00 bn	.00 bn	.00 bn	.00 bn	.40 bn		Apr24	67,983.1	3,674,765	0.3
				Contingency					.00 bn	.00 bn	.00 bn	.04 bn	.00 bn	.00 bn	.00 bn	.00 bn	.00 bn	.00 bn	.00 bn	.00 bn	.06 bn		May24	67,983.1	3,674,765	0.3
				Jun24	90,644.2	4,899,686	0.4
				Pg2Pj1					.28 bn	.22 bn	.33 bn	.17 bn	.17 bn	.65 bn	.74 bn	.48 bn	.37 bn	.16 bn	.02 bn	.00 bn	3.59 bn		Jul24	105,526.6	5,704,139	0.3
				Pg2Pj2					.00 bn	.00 bn	.01 bn	.11 bn	.01 bn	.00 bn	.00 bn	.00 bn	.00 bn	.00 bn	.00 bn	.20 bn	.00 bn		Aug24	105,526.6	5,704,139	0.3
				Pg2Pj3					.00 bn	.00 bn	.00 bn	.11 bn	.01 bn	.01 bn	.01 bn	.00 bn	.00 bn	.00 bn	.00 bn	.20 bn	.33 bn		Sep24	140,702.1	7,605,519	0.4
				Oct24	252,987.0	13,674,975	0.4
				Pg2: 150MW Gas Engine Carbon Copies	ZAR					4.8 m	6.9 m	6.9 m	108.4 m	8.1 m	8.1 m	7.8 m	.2 m	.2 m	.2 m	.2 m	200.2 m	351.8 m		Nov24	252,987.0	13,674,975	0.4
				P21: Planning					4,800k					4,800k		Dec24	126,493.5	6,837,488	0.2
				P21: Engineering					7,595k	7,595k	7,595k	7,595k					30,378k		Y2025	2,222,917.5	120,157.7
				P21: Drilling					6,150k	6,150k					12,300k		Jan25	65,169.9	3,522,695	0.3
				P21: Studies					605k	605k	605k					1,814k		Feb25	65,169.9	3,522,695	0.3
				P21: Licences & Approvals					288k	288k					576k		Mar25	86,893.1	4,696,926	0.4
				P21: Overheads					173k	173k	173k	173k	173k	173k	173k	173k	173k	173k	173k	1,902k		Apr25	208,559.1	11,273,467	0.3
				P21: Procurement					100,000k					200,000k	300,000k		May25	208,559.1	11,273,467	0.3
				P21: Execution					k		Jun25	278,078.9	15,031,290	0.4
				Jul25	236,035.7	12,758,685	0.3
				Pg2: 150MW Gas Engine Carbon Copies					.0 m	.2 m	6.3 m	113.9 m	8.1 m	.5 m	.2 m	.2 m	.2 m	.2 m	.2 m	200.2 m	330.0 m		Aug25	236,035.7	12,758,685	0.3
				P22: Planning					k		Sep25	314,714.2	17,011,581	0.4
				P22: Engineering					7,595k	7,595k					15,189k		Oct25	209,480.8	11,323,284	0.4
				P22: Drilling					6,150k	6,150k					12,300k		Nov25	209,480.8	11,323,284	0.4
				P22: Studies					k		Dec25	104,740.4	5,661,642	0.2
				P22: Licences & Approvals					288k	288k					576k		Y2026	552,869.5	29,884.8
				P22: Overheads					173k	173k	173k	173k	173k	173k	173k	173k	173k	173k	173k	1,902k		Jan26	110,486.3	5,972,231	0.3
				P22: Procurement					100,000k					200,000k	300,000k		Feb26	110,486.3	5,972,231	0.3
				P22: Execution					k		Mar26	147,315.0	7,962,975	0.4
				Apr26	48,856.5	2,640,890	0.3
				Pg2: 150MW Gas Engine Carbon Copies					.0 m	.2 m	.2 m	106.3 m	6.6 m	8.1 m	7.8 m	.2 m	.2 m	.2 m	.2 m	200.2 m	330.0 m		May26	48,856.5	2,640,890	0.3
				P23: Planning					k		Jun26	65,142.0	3,521,187	0.4
				P23: Engineering					7,595k	7,595k					15,189k		Jul26	6,461.0	349,245	0.3
				P23: Drilling					6,150k	6,150k					12,300k		Aug26	6,461.0	349,245	0.3
				P23: Studies					k		Sep26	8,614.7	465,660	0.4
				P23: Licences & Approvals					288k	288k					576k		Oct26	76.1	4,112	0.4
				P23: Overheads					173k	173k	173k	173k	173k	173k	173k	173k	173k	173k	173k	1,902k		Nov26	76.1	4,112	0.4
				P23: Procurement					100,000k					200,000k	300,000k		Dec26	38.0	2,056	0.2
				P23: Execution					k

				Pg3: 300MW Turbine PowerGen					.0 m	5.4 m	18.4 m	200.0 m	.0 m	.0 m	.0 m	.0 m	.0 m	.0 m	.0 m	.0 m	223.8 m
				Pg3: Planning					4,800k					4,800k
				Pg3: Engineering					17,359k					17,359k
				Pg3: Drilling					k
				Pg3: Studies					605k	605k					1,210k
				Pg3: Licences & Approvals					288k					288k
				Pg3: Overheads					173k					k	k	k	k	k	173k
				Pg3: Procurement					200,000k					200,000k
				Pg3: Execution					k

				Pg4: 1950bbl GTL					.0 m	.6 m	5.4 m	222.9 m	41.6 m	41.6 m	41.0 m	41.0 m	.2 m	.2 m	.2 m	.2 m	395.0 m
				Pg4: Planning					4,800k	4,800k					9,600k
				Pg4: Engineering					17,359k	34,718k	34,718k	34,718k	34,718k			k	k	156,230k
				Pg4: Drilling					6,150k	6,150k	6,150k	6,150k			k	k	24,600k
				Pg4: Studies					605k	605k	605k	605k	605k					3,024k
				Pg4: Licences & Approvals					k
				Pg4: Overheads					173k	173k	173k	173k	173k	173k	173k	173k	173k	1,556k
				Pg4: Procurement					200,000k					200,000k
				Pg4: Execution					k

				inflation					1.06	1.06	1.06	1.06	1.06	1.06	1.06	1.06
				2014	2015	2016	2017	2018	2019	2020	2021	2022	2023	2024	2025	2026
				Engineering					48,465,500	51,373,430	54,455,836	57,723,186	61,186,577	64,857,772	68,749,238	72,874,192	77,246,644	81,881,442	86,794,329	92,001,989	97,522,108
				Drilling					6,865,500	7,277,430	7,714,076	8,176,920	8,667,536	9,187,588	9,738,843	10,323,174	10,942,564	11,599,118	12,295,065	13,032,769	13,814,735
				Studies					5,065,500	5,369,430	5,691,596	6,033,092	6,395,077	6,778,782	7,185,509	7,616,639	8,073,637	8,558,056	9,071,539	9,615,831	10,192,781
				Management					8,465,500	8,973,430	9,511,836	10,082,546	10,687,499	11,328,749	12,008,474	12,728,982	13,492,721	14,302,284	15,160,421	16,070,046	17,034,249
				Procurement					965,500	1,023,430	1,084,836	1,149,926	1,218,922	1,292,057	1,369,580	1,451,755	1,538,860	1,631,192	1,729,063	1,832,807	1,942,776
				Support Svcs					965,500	1,023,430	1,084,836	1,149,926	1,218,922	1,292,057	1,369,580	1,451,755	1,538,860	1,631,192	1,729,063	1,832,807	1,942,776
				Licencs etc					1,965,500	2,083,430	2,208,436	2,340,942	2,481,398	2,630,282	2,788,099	2,955,385	3,132,708	3,320,671	3,519,911	3,731,106	3,954,972
				Contingencies					10,965,802	11,623,750	12,321,175	13,060,446	13,844,072	14,674,717	15,555,200	16,488,512	17,477,823	18,526,492	19,638,081	20,816,366	22,065,348
				Total:					83,726,316	101,287,572	148,402,338	1,264,560,803	202,676,087	211,907,095	216,555,546	208,492,411	134,310,372	142,317,003	150,804,030	759,800,280	2,380,863,328
				1.21	1.77	15.10	2.42	2.53	2.59	2.49	1.60	1.70	1.80	9.07	28.44
				execution					2.50 bn					3.50 bn			4.42 bn
				B-BEEE costs

				Assumptions:					Coal: 5mt measured from 2013/4 drilling (about 50ha); 27mt inferred
				Consider using dir-drilling to check coal in areas around the farms
				This should be enough to take care of needs for 5-10 years, including CTL
				We can extend gasifiers to be 2km/400m thus doubling the life of a gasifier
				Procurement: pay refundable deposits in Y1; place firm orders starting in Y2
				Pg2 Pj1,2,3 executed in staggered parallel

## Sheet1
#VALUE!
					Pg
					Pg1	50MW power